## Sprint 1 Backlog
Story # | Sprint Backlog Item | Task # | Volunteer | Task Details | Initial Effort Estimate (hrs) | New Estimates of Effort remaining at end of | [6 empty] | Status
[6 empty] | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
US001 | As a Patient-account executive /cashier / manager I want to be able to log in the Hospital website with my user ID and password So that I carry out different operations | Task 1 | Megha | Write java program for log in verification. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 2 | Rashmi | Design the UI for the log in page | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 3 | Shivam | Design and create the DB fields | 1 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 4 | Raksha | Write test conditions to test the home page | 1 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 5 | Sanchit | Create validation for username & password. | 1 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
|  | Task 6 | Megha | Integrate the different designs and back-end. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0 | Closed
224
US002 | As a Patient-account executive I want to be able to capture new Patient information So that I can create a new Patient in the system | Task 1 | Rashmi | Write a java program for getting data entered for Patient registration | 4 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Megha | Design & create DB fields. | 2 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Sanchit | Create validation for all the fields. | 3 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | Shivam | Test the conditions for creating a new Patient. | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 1; New Estimates of Effort remaining at end of Day3: 2 | Closed
|  | Task 5 | Raksha | Design UI for the create patient Page. | 3 | New Estimates of Effort remaining at end of Day1: 1; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 6 | Megha | Integrate the different designs and back-end. | 3 | 0 | 0 | 0 | 4 | 0 |  |  | Closed
US003 | As a Patient-account executive I want to be able to edit existing Patient information So that I can store the updated Patient information in the system | Task 1 | Sanchit | Write java program for searching patient in DB. | 3 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Megha | Write java program for updating patient info in DB. | 5 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Rashmi | Create UI for searching Patient. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 4 | Raksha | Create UI for updating Patient. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 5 | Shivam | Write DB queries for updating DB. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 6 | Sanchit | Create validation for checking entered data. | 2 | New Estimates of Effort remaining at end of Day1: 2; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 7 | Megha | Integrate all the different parts in one. | 4 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 0 | Closed
US004 | As a Patient-account executive I want to be able to delete existing Patient from system | Task 1 | Megha | Write java program for deleting the Patient. | 7 | New Estimates of Effort remaining at end of Day1: 3; New Estimates of Effort remaining at end of Day2: 4; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Sanchit | Design UI for Patient deletion. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 3 | Shivam | Write DB queries for deleting the Patient. | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 3; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 4 | Raksha | Test if the deletion works properly. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 1; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 5 | Megha | Integrate all the tasks into one. | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 3; New Estimates of Effort remaining at end of Day4: 0 | Closed
US005 | As a Patient-account executive I want to be able to view the status of all the patients of the hospital | Task 1 | Sanchit | Create UI for showing the status of all the patients. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 2; New Estimates of Effort remaining at end of Day3: 0 | Closed
|  | Task 2 | Shivam | Write java program for getting the details from DB. | 6 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 3; New Estimates of Effort remaining at end of Day3: 4; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 3 | Rashmi | Write DB queries for fetching all the patient details. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 4 | Raksha | Test if all the Patients are fetched or not. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 5 | Megha | Combine the UI, java program and DB. | 3 | 0 | 0 | 0 | 4 | 0 |  |  | Closed
US006 |  | Task 1 | Megha | Design UI for Issuing Medicines. | 3 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 3 | Closed
| As a patient-account executive I want to be able to issue medicines to the Patient. | Task 2 | Rashmi | Write java program for storing the entered Medicines. | 3 | 0 | 0 | 2 | 1 | 0 |  |  | Closed
|  | Task 3 | Rashmi | Write DB queries for issuing medicines. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2 | Closed
|  | Task 4 | Megha | Check validations of input data. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2 | Closed
|  | Task 5 | Sanchit | Test the input doesn't duplicate data. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2 | Closed
|  | Task 6 | Raksha | Integrate all the above tasks together. | 3 | 0 | 0 | 0 | 4 | 0 |  |  | Closed
|  | Task 7 | Shivam | Design UI for showing success or error message. | 1 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 1 | Closed
US007 | As a Patient-account executive I want to be able to add diagnostics for a Patient. | Task 1 | Rashmi | Design UI for adding diagnostics. | 2 | New Estimates of Effort remaining at end of Day1: 0; New Estimates of Effort remaining at end of Day2: 0; New Estimates of Effort remaining at end of Day3: 2; New Estimates of Effort remaining at end of Day4: 0 | Closed
|  | Task 2 | Sanchit | Design UI for diagnostics conducted. | 2 | 0 | 0 | 0 | 2 | 0 |  |  | Closed
|  | Task 3 | Shivam | Design UI for showing success or error message. | 3 | 0 | 0 | 0 | 3 | 0 |  |  | Closed
|  | Task 4 | Raksha | Write java program for searching tests in DB. | 3 | 0 | 0 | 0 | 3 | 0 |  |  | Closed
|  | Task 5 | Megha | Write java program for selecting a test in and adding it to the patients table in db. | 5 | 0 | 0 | 0 | 4 | 0 |  |  | Closed
|  | Task 6 | Sanchit | Test the program if it executes properly. | 2 | 0 | 0 | 0 | 2 | 0 |  |  | Closed
|  | Task 7 | Megha | Integrate all the sections. | 4 | 0 | 0 | 0 | 0 | 4 | 0 |  | Closed
US008 | As a Patient-account executive I want to be able to view final bill for the patient. | Task 1 | Shivam | Create UI for Final Billing page. | 4 | 0 | 0 | 0 | 3 | 1 | 0 |  | Closed
|  | Task 2 | Sanchit | Write java program for getting the details from DB. | 4 | 0 | 0 | 0 | 2 | 2 | 0 |  | Closed
|  | Task 3 | Raksha | Write DB queries for fetching all pharmacy charges. | 3 | 0 | 0 | 0 | 0 | 3 | 0 |  | Closed
|  | Task 4 | Rashmi | Write DB queries for fetching all diagnostics charges. | 3 | 0 | 0 | 0 | 0 | 3 | 0 |  | Closed
|  | Task 5 | Megha | Combine the UI, java program and DB. | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Closed
US009
US010
US011
US012
US013
US014
|  |  |  | Total | 135 | 31 | 30 | 31 | 32 | 13 | 5 | 0

## Sprint 1 Burndown Chart
Day0 | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7
224 | 192 | 160 | 128 | 96 | 64 | 32 | 0
224 | 193 | 163 | 132 | 100 | 68 | 36 | 4